## Slide 1: Karnataka Team
Summary of projects on hand
Presented at the Governing Body Meeting September 5, 2023
Convergence of Gram Panchayats and Self Help Groups
Promotion of Sports activities in Gram Panchayats
Gram Arogya (Public Health)
Concurrent evaluation of MGNREGA Crèches
Evaluation of Rural Libraries
Institutional strengthening of Social Audit Unit

## Slide 2: Field Visits – A Critical Learning Tool for the Fellows
More than 90 Combined Field work days (3 Fellows plus State Lead) in 5.5 months (does not include the six weeks of election code of conduct)
Our aim: all should have knowledge of all the projects in our portfolio
  Each may have a main project and 1-2 other secondary projects at a time
Crèches
Libraries
SWM

## Slide 3: Field Visits – A Critical Learning Tool for the Fellows
  The team visited:
  21 Districts | 39 Taluks |67 Gram Panchayats
35 SWM Teams
51 Libraries
16 Crèches

## Slide 4: Field Visits – A Critical Learning Tool for the Fellows
  Learnings from the field are reflected in the reports produced by the team
    RDPR is operationalizing some of the recommendations based on field level findings
    Now commissioned other smaller evaluation projects

## Slide 5: Gratitude
  The Karnataka Team thanks our mentors for their continued and in-depth engagement with the team on all aspects of our work
  They are available not just on the weekly meetings, but any time we want to run an idea or a situation by them for feedback and advice.
Weekly Meetings / Mentoring

## Slide 6
  Submitted the Concurrent Evaluation report in July.
  Discussed with Commissioner
    Signs of implementing recommendations
  NGO tie ups being planned for some key recommendations like:
    additional libraries in smaller villages to mitigate distance and transport issues
    librarian upskilling and,
    replenishment of books.
Evaluation of Rural Libraries
Link to Report

## Slide 7
  Larger Outcome evaluation (mentioned in the MoU) is in the works.
    Theory of Change and Logframe submitted for internal review
    Draft Questionnaire undergoing revisions.
  Concurrent evaluation of Digital Libraries (implemented by Sikshana Foundation with Dell Foundation Grant)
  We are currently working on this – focus is on field level insights to inform scale up
Evaluation of Rural Libraries

## Slide 8
Evaluation of NREGA Crèches
Link to Report
  RDPR launched Pilot Crèches in 2022 (two in each district)
  Field insights on how the pilot crèches were functioning.
  Not all were functioning; we visited 16 and reported to the department in June
  The findings will inform the current roll out of 4000 crèches (in four phases).

## Slide 9
Evaluation of NREGA Crèches – Baseline Study
  This year, RDPR hopes to roll out 4000 crèches in rural areas
  Baseline study in a sample of the Gram Panchayats slated for the first phase of roll out shortly
  Theory of Change and Questionnaire are ready and have been discussed internally and with the Commissioner

## Slide 10
Evaluation of NREGA Crèches – Baseline Study
  Sampling procedures
  The first thousand crèches will be in the Kalyana Karnataka region
    Appropriate sampling procedures planned
    Mode of data collection – Potential to use students from RDPR University, Gadag
    Ideal to do two districts first, to enable course corrections if required. Still being discussed

## Slide 11
Evaluation of NREGA Crèches – Implementation
  CRISP Involvement:
  If department asks for monitoring, team can help with continuous monitoring and reporting on implementation (will need dedicated resources)
  Support the department in roll out – Review of GO and circulars
  Recommend and implement digital record keeping at the crèche level.

## Slide 12: Solid Waste Management (SWM)
  By far, the most challenging project on our list
  Extensive field visits to study SWM through SHGs
  Key observations relate to:
    Whether the initiative enables an enterprise or entrepreneur model for the SHG women
    Whether they are able to monetize the waste collected
    Whether citizens will pay for the waste collection service
    Infrastructure needed for waste processing
SHG - GP Convergence

## Slide 13: Solid Waste Management (SWM)
SHG - GP Convergence
  In the next six months:
  Team will select 2-3 “Resource Clusters” – GPs where some interventions can be tried out:
  Work with GPs for formally authorizing women to collect user fees. Achieve higher user fee collection
  Mapping of local scrap dealers for decentralized management of waste
  Explore additional income-generating activities for women around waste management

## Slide 14: Solid Waste Management (SWM)
SHG - GP Convergence
  In the next six months:
  Nurture leadership among the women involved in SWM
    Recommend a Supervisor role within the SWM group
  Develop templates for record-keeping and train the women to use them
    Amount of user fees collected, by month and user
    Amount of waste collected
    Amount of waste sold; earnings
    Explore digital record maintenance through an app
  Greater engagement with public for sensitization on proper handling of waste

## Slide 15
Formerly known as Gram Panchayat Arogya Amrutha Abhiyana (GPAAA)
Grama Arogya focus – NCD testing, TB screening, Anaemia screening, mental health counselling and awareness raising on child marriage and menstrual hygiene
GP Health management kits distributed, health camps are conducted
Strengthening Grama Arogya

## Slide 16
Team focus:
Scoping visits to Grama Arogya camps in Bagalkote and Dakshin Kannada districts
To study the processes, data management, extent of GP involvement, coordination between GP and Health providers at the GP level
User interaction to probe improvement, if any in the health-seeking behaviour of the people
Strengthening Grama Arogya

## Slide 17
Next steps:
Strengthening Grama Arogya
More visits to camps – sample to cover more districts
Interview camp attendees to study health-seeking behaviour / follow up after camp
Interview of PDOs and CHOs
Data analysis
Preparation of concurrent evaluation report

## Slide 18
  External team of experts commissioned by CRISP to conduct an evaluation of the Social Audit Unit
  Test audit in two Gram Panchayats to assess quality of Social Audits in Karnataka
  Final Report with findings from the Test Audits submitted to the government
  (Prepared by external team)
Strengthening the Social Audit Unit

## Slide 19
  Proposed: 51 Fellows will be recruited for deployment at Taluk level in the Kalyana Karnataka Region.
  With mentors’ guidance and inputs, prepared a concept note on the Commissioner’s request.
  Commissioner has called for a meeting to brainstorm and lay a framework for the Fellowship
  CRISP will assist the government with recruitment of Fellows and program management through a PMU.
Proposed: CM’s Rural Development Fellowship

## Slide 20: Centre for Child Responsive Local Governance
  Our team wrote the proposal to UNICEF and prepared the budget
  Prepared Job Descriptions for the Consultants and Young Professionals that were hired for the Centre
  Created the Results Matrix
  Put in sports as an important indicator of child responsive governance
Other projects / tasks assigned by RDPR

## Slide 21: Proposals for Funding for Rural Libraries
  Team members wrote 6-8 proposals for funding of Rural Libraries
    Preparatory work
    Research
    Budgets
    Revisions based on feedback
  Assisted the Minister’s office to develop CSR proposals for funding
Other projects / tasks assigned by RDPR

## Slide 22: Document Preparation
  Team members participate in:
  Government Order Preparation
  1 or 2-day long “WriteShops” for various documents and project specifications
  Coordination with NGOs assisting the Government with the above
Other projects / tasks assigned by RDPR

## Slide 23: Review of NGO Proposals to the Department
  Commissioner asks CRISP to evaluate NGO proposals to the Department for various initiatives:
  Assess service offered by the NGO
  Evaluate the proposal on various parameters
  Assist the department in discussions with the NGO on implementation
Other projects / tasks assigned by RDPR

## Slide 24: We started an excel sheet to document tasks given to us by the Commissioner’s office or the ACS.