## Sheet1
GANTT CHART FOR GP-SHG CONVERGENCE
*** This Chart is to be read in conjunction with the Activities listed in the Action Plan 2023-24
|  | April- June 2023 |  |  | July- Sept 2023 |  |  | Oct-Dec 2023 |  |  | Jan-March 2024
S.No. | Activity | April | May | June | July | August | Sept | Oct | Nov | Dec | Jan | Feb | March
1 | Setting the vision for convergence
1.1 | Develop a vision for convergence
1.2 | Understanding the status, processes and situation
1.3 | Study and documentation of good practices
1.4 | Liaison with partner organisations
2 | Formation/ working of State Resource Group
2.1 | Identification of experts
2.2 | Working on training modules
3 | Orientation of Sanjeevini-SRLM staff
3.1 | Training and Capacity Buidling
3.2 | Collating the feedback
4 | Training of Trainers
4.1 | Formation of a team of trainers
4.2 | ToT
5 | Conducting scoping study
5.1 | Develop questionnaire for scoping study
5.2 | Conduct Interviews and FGDs
5.3 | Devise strategy for implementation
5.4 | Devise model Joint Plan of Action
5.5 | Identification of entry-point activities
5.6 | Identification of pilot GPs
5.7 | Listing of best practices
5.8 | Identification of LRG
6 | Planning exposure visits
6.1 | Develop structured exposure visit programme
6.2 | Visit to model GPs, within and outside the state
7 | Capacity Building of Local Resource Group
7.1 | Identification of members of LRG
7.2 | Training of LRG
8 | Strengthening the SHG Network
8.1 | Capacity Building of SHGs and their federations on various aspects
8.2 | Work with the dept. to enforce policy directives on community-based monitoring and social audit of schemes/ programmes by SHGs
8.3 | Mobilisation of all poor households into SHGs
9 | Capacity Building of Panchayats
9.1 | Training programmes to GP functionaries and ERs
9.2 | Exposure visits
10 | Entry-point activities
10.1 | Demand generation and planning
10.2 | Labour budget preparation by SHGs and strengthening Gram Sabhas
10.3 | Organising campaigns by SHGs and GPs
11 | Engagement in Gram Sabhas
11.1 | Informed participation and participatory assessment of entitlements
11.2 | Functional Gram Sabhas
12 | Using Participatory Assessment and Planning Tools
12.1 | Setting up of baseline data
12.2 | Status studies and surveys by SHGs
12.3 | Planning based on PAE
12.4 | Monitoring of entitlement access
13 | Strengthening the institutional capacity of GPLF
13.1 | Capacity building of GPLF members on various aspects of institutional capacity
14 | Strengthening/ establishing GPCC
14.1 | Formation/ strengthening GPCC
14.2 | Working of GPCC
15 | Formation of a team of Community Professionals
15.1 | Engaging CPs for taking the project to non-pilot locations